## Sheet1
Bug ID | Bug Description | Environment | Steps to Reproduce | Source URL | Expected Result | Actual Result | Severity | Priority | Status | Possible Solution | Evidence | Assigned To
ATC_0001 | • "Add to Cart" button not working on mobile devices | • Android, Chrome v112 | 1. Open the website on a mobile phone (Chrome browser) 2. Navigate to the product page 3. Tap the "Add to Cart" button | www.jiji.ng | • Item should be added to cart and confirmation message displayed | • Button shows loading spinner but nothing happens | High | High | • In progress | • check the code | https://photos.app.goo.gl/qdXGVPDTqDATJskj9 | • Ibironke Yekini
ATC_0002 | • Cart count does not update when item is removed | • Windows 10, Chrome v112 | 1. Add 2 items to the cart 2. Go to cart page 3. Click “Remove” next to one item | www.jiji.ng | • Cart count in the header should change from 2 to 1 | • Item is removed but cart count still shows 2 | Medium | High | • In progress | • check the code | https://photos.app.goo.gl/eUafx19soSiK1RxTA | • Kolawole Kabiru